## Overview
AGING GRACEFULLY — Development, Testing & Launch Schedule
5 Phases · 36 months · MVP launch at Month 9
Phase / Milestone | Description | Start | End | Duration | Status | Key deliverables
PHASE 0 — FOUNDATION
0.1 Team assembly | Hire founding engineering team: 2 fullstack, 1 backend, 1 mobile, 1 design, 1 DevOps, 1 QA | Month 1 | Month 2 | 2 mo | Planning | Offer letters signed; onboarding complete
0.2 Infrastructure setup | AWS org, VPC, RDS Aurora, S3, CI/CD pipelines (GitHub Actions + ArgoCD), Terraform IaC baseline | Month 1 | Month 2 | 2 mo | Planning | All environments provisioned; IaC in source control
0.3 Auth & identity foundation | Auth0 tenant, MFA flows, RBAC model, JWT infrastructure, session management | Month 2 | Month 3 | 2 mo | Planning | Auth service deployed; MFA tested
0.4 Design system | Figma component library, design tokens, accessibility annotations, WCAG 2.2 AA audit framework | Month 1 | Month 2 | 2 mo | Planning | Design system published; all components annotated
0.5 Security baseline | WAF, secrets management (AWS Secrets Manager), network segmentation, HIPAA gap assessment, BAA with AWS | Month 1 | Month 3 | 3 mo | Planning | SOC2 Type I gap assessment; AWS BAA signed
0.6 Legal & compliance | Privacy policy, ToS, HIPAA counsel engaged, BAA templates drafted, TCPA/10DLC SMS registration | Month 1 | Month 2 | 2 mo | Planning | Legal docs approved; 10DLC brand registration submitted
0.7 Data architecture | PostgreSQL schema v1, encryption key management (KMS), audit log schema, FHIR data partition design | Month 2 | Month 3 | 2 mo | Planning | Schema migrated; encryption validated; audit log live
PHASE 1 — MVP
Sprint 1–2 (Wk 1–4): Vault foundation | Document upload, S3 storage with SSE-KMS, auto-categorization ML model, metadata schema, profile creation | Month 3 | Month 4 | 2 mo | Not started | File upload with progress; auto-cat with >80% accuracy; profile CRUD
Sprint 3–4 (Wk 5–8): Vault features | Smart tagging UI, document checklist, expiration alerts, multi-person profiles, basic permissions model | Month 4 | Month 5 | 2 mo | Not started | Checklist live; expiry email alerts; 2-person vault sharing
Sprint 5–6 (Wk 9–12): Health Hub core | Health profile builder, medication tracker, provider directory, appointment log, screening schedule engine | Month 5 | Month 6 | 2 mo | Not started | Medication tracker with reminders; provider list; screening calendar
Sprint 7–8 (Wk 13–16): AI assistant v1 | Claude API integration, document Q&A, health profile Q&A, PII stripping pipeline, streaming response UI | Month 6 | Month 7 | 2 mo | Not started | AI answers document questions; PII never in LLM logs; <4s P95
Sprint 9–10 (Wk 17–20): Stage navigator | 5-stage care model content, warning signs library, milestone conversation guides, normal vs. concern guide | Month 7 | Month 8 | 2 mo | Not started | All 5 stages with content; 12 conversation guides published
Sprint 11 (Wk 21–22): Emergency share | One-tap emergency packet (PDF generation), time-limited share links, offline cache for mobile | Month 8 | Month 8 | 1 mo | Not started | Emergency packet generated in <5s; share link with 48hr TTL
Sprint 12 (Wk 23–24): MVP polish & hardening | Performance optimization, a11y audit pass, cross-browser testing, load testing, bug bash, security scan | Month 8 | Month 9 | 2 mo | Not started | LCP<2.5s; Lighthouse a11y >95; 0 P0/P1 bugs; pen test passed
MVP Alpha testing (internal) | Dog-fooding with team + advisors; structured feedback sessions; issue triage | Month 8 | Month 9 | 2 mo | Not started | Alpha test report; P0 bug list resolved
MVP Beta testing (50 families) | Closed beta with 50 recruited caregiver families; NPS measurement; accessibility user testing | Month 9 | Month 9 | 1 mo | Not started | NPS baseline; beta feedback synthesized; go/no-go decision
MVP LAUNCH | Public launch — web app + iOS + Android | Month 9 | Month 9 | 1 mo | Not started | Press release; Product Hunt launch; 1,000 user target Month 1
PHASE 2 — GROWTH
Care Finder v1 | Facility search & directory (Google Places + CMS Care Compare data), care type explainers, facility comparison tool | Month 10 | Month 12 | 3 mo | Not started | Search live in all 50 states; CMS star ratings integrated
Care Finder v2 | Facility tour checklist, red flags guide, in-home agency directory, save & shortlist feature, transition guides | Month 12 | Month 13 | 2 mo | Not started | Tour checklist; agency search; shareable shortlist
Money & Coverage v1 | Medicare explainer, LTC insurance guide, cost estimator (Genworth data), benefits finder (VA, PACE, LIS) | Month 10 | Month 12 | 3 mo | Not started | Medicare guide; cost estimator by state; VA benefits screener
Money & Coverage v2 | Medicaid navigator, caregiver tax guide, insurance portal API v1, open enrollment reminders | Month 13 | Month 15 | 3 mo | Not started | Medicaid state rules; EOB decoder; OEP reminder flow
Family Workspace | Multi-member invitations, shared care log, task delegation, sibling coordination, family messaging | Month 11 | Month 13 | 3 mo | Not started | 3+ family members in shared workspace; task assign & complete
SMS parent interface v1 | Twilio integration, outbound medication & appointment reminders, STOP/opt-out, keyword response parser, 10DLC approval | Month 11 | Month 14 | 4 mo | Not started | SMS reminders live; 2-way keyword responses; TCPA compliant
SMS parent interface v2 | WhatsApp Business API, MMS document delivery, secure document links, check-in messages, family relay | Month 14 | Month 16 | 3 mo | Not started | WhatsApp live; document delivery via MMS; check-in with escalation
Voice call layer | Twilio Voice + Polly TTS, automated medication reminder calls, DTMF responses, voicemail transcription | Month 15 | Month 17 | 3 mo | Not started | Outbound voice calls; keypad confirm; transcription to caregiver
Plan for Yourself v1 | Aging plan builder wizard, advance directive builder (state templates), healthcare proxy guide, wishes journal | Month 12 | Month 15 | 4 mo | Not started | AD builder for all 50 states; plan wizard complete; journal
Plan for Yourself v2 | Financial POA guide, LTC insurance evaluator, home modification planner, estate checklist | Month 15 | Month 17 | 3 mo | Not started | Full self-planning suite live
FHIR integration v1 | Epic + Cerner app registration, SMART on FHIR auth flow, ingestion pipeline, normalization layer, Health Hub surface | Month 13 | Month 18 | 6 mo | Not started | Epic & Cerner connected; medications/conditions/labs auto-imported
AI assistant v2 | Personalized guidance (profile-aware), conversation prep assistant, medication explainer, proactive nudges, summary generator | Month 14 | Month 17 | 4 mo | Not started | Profile-aware answers; appointment prep; weekly nudge digest
DocuSign integration | eSign integration for advance directives, POA docs, facility contracts; auto-file to Vault on completion | Month 16 | Month 17 | 2 mo | Not started | Sign & file advance directive in-platform
Phase 2 QA sprint | Full regression testing, load test (10k concurrent), a11y audit, security pen test #2, WCAG audit by 3rd party | Month 17 | Month 18 | 2 mo | Not started | Zero P0/P1; Lighthouse a11y >97; pen test clean; WCAG report
Phase 2 milestones | 10,000 active families; $1M ARR; NPS >65; employer pilot launched (5 companies) | Month 18 | Month 18 | 1 mo | Not started | ARR dashboard; employer dashboard live
PHASE 3 — SCALE
Employer benefit channel | SSO/SAML integration, Teams + Slack bots for nudges, HR admin dashboard, usage reporting, bulk onboarding | Month 19 | Month 22 | 4 mo | Not started | 20 employer accounts; HR dashboard; SAML SSO live
Alexa skill v1 | Alexa Skills Kit integration, proactive medication reminders via Alexa, family message delivery, check-in responses | Month 19 | Month 21 | 3 mo | Not started | Alexa skill certified; proactive reminders; 2-way check-ins
Google Home action | Google Actions SDK, same feature parity as Alexa skill, Nest Hub display support | Month 21 | Month 23 | 3 mo | Not started | Google action approved; full feature parity with Alexa
AI voice conversation | Deepgram STT + Claude streaming + Polly TTS for 2-way voice AI calls, emergency keyword detection | Month 22 | Month 25 | 4 mo | Not started | Voice AI conversation live; emergency detection accuracy >95%
FHIR expansion v2 | Athenahealth, Allscripts, eClinicalWorks, CMS Blue Button 2.0, CommonWell connection | Month 20 | Month 24 | 5 mo | Not started | 8+ EHR systems connected; Blue Button live for Medicare users
Pharmacy / Surescripts API | Active prescription pull from pharmacy network, refill auto-alerts, cross-pharmacy reconciliation | Month 22 | Month 25 | 4 mo | Not started | Prescriptions auto-imported from major pharmacy chains
Trusted provider marketplace | Eldercare attorneys, GCMs, senior move managers: vetted directory, booking integration, referral revenue tracking | Month 21 | Month 24 | 4 mo | Not started | 500 vetted providers; in-platform booking; revenue reporting
Mobile app v2 | Native iOS/Android rebuild (Swift/Kotlin), biometric auth, document scanner, offline vault, widget support | Month 20 | Month 25 | 6 mo | Not started | App Store rating >4.5; offline vault; camera scanner
Plaid financial integration | Read-only bank/investment account view, anomaly detection for elder financial abuse, care cost tracking | Month 23 | Month 26 | 4 mo | Not started | Financial safety alerts; balance view; cost vs. budget tracker
Community & peer support | Moderated caregiver forums, peer matching by care situation, expert Q&A (social workers, eldercare attorneys) | Month 24 | Month 26 | 3 mo | Not started | 1,000 active forum members; weekly expert Q&A
Phase 3 QA & scale testing | Load test (100k concurrent), chaos engineering, disaster recovery drill, full a11y re-audit, SOC2 Type II observation begins | Month 25 | Month 27 | 3 mo | Not started | 99.9% uptime validated; DR RTO <1hr; SOC2 audit started
Phase 3 milestones | 50,000 active families; $5M ARR; 100 employer accounts; profitable unit economics | Month 27 | Month 27 | 1 mo | Not started
PHASE 4 — EXPANSION
SOC 2 Type II certification | Complete SOC 2 Type II audit (12-month observation period); publish VPAT 2.4 accessibility conformance report | Month 28 | Month 30 | 3 mo | Not started | SOC 2 Type II report issued; VPAT published
Clinical partnership program | EHR-embedded care coordination tools, hospital discharge planning integration, ACO/MSSP partnerships | Month 28 | Month 32 | 5 mo | Not started | 3 health system partnerships; embedded workflow live
Predictive health insights | ML models for care transition prediction, hospitalization risk, medication adherence forecasting | Month 29 | Month 33 | 5 mo | Not started | Risk scores for transition prediction (AUC >0.75)
Platform API (developer) | Public API for eldercare app ecosystem, webhooks, sandbox environment, developer documentation | Month 30 | Month 33 | 4 mo | Not started | Public API GA; 10 third-party integrations
International — Canada | PIPEDA compliance, provincial health record integration, French language support (Quebec) | Month 30 | Month 34 | 5 mo | Not started | Canada launch; French content complete
International — UK | GDPR/UK GDPR compliance, NHS record integration (GP Connect FHIR), UK care provider directory | Month 32 | Month 36 | 5 mo | Not started | UK launch; NHS integration live
Phase 4 milestones | 150,000 active families; $20M ARR; SOC2 certified; Series B fundraise | Month 36 | Month 36 | 1 mo | Not started
STATUS LEGEND
Planning
Not started
In Progress
Complete

## Gantt Chart
AGING GRACEFULLY — Development Gantt (36 months)
|  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 Y2 |  |  | Q2 Y2 |  |  | Q3 Y2 |  |  | Q4 Y2 |  |  | Q1 Y3 |  |  | Q2 Y3 |  |  | Q3 Y3 |  |  | Q4 Y3
Phase / Milestone | Type | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
PHASE 0 — FOUNDATION
Team assembly | Dev
Infrastructure setup | Dev
Auth & identity | Dev
Design system | Dev
Security baseline | Dev
Legal & compliance | Dev
Data architecture | Dev
PHASE 1 — MVP
Vault foundation (Spr 1–2) | Dev
Vault features (Spr 3–4) | Dev
Health Hub core (Spr 5–6) | Dev
AI assistant v1 (Spr 7–8) | Dev
Stage Navigator (Spr 9–10) | Dev
Emergency share (Spr 11) | Dev
MVP polish & hardening (Spr 12) | Dev
Alpha testing | Test
Beta testing (50 families) | Test
MVP LAUNCH | Launch | [8 empty] | ▲
PHASE 2 — GROWTH
Care Finder v1 | Dev
Care Finder v2 | Dev
Money & Coverage v1 | Dev
Money & Coverage v2 | Dev
Family Workspace | Dev
SMS parent interface v1 | Dev
SMS parent interface v2 | Dev
Voice call layer | Dev
Plan for Yourself v1 | Dev
Plan for Yourself v2 | Dev
FHIR integration v1 | Dev
AI assistant v2 | Dev
DocuSign integration | Dev
Phase 2 QA sprint | Test
Phase 2 milestone ✓ | Launch | [17 empty] | ▲
PHASE 3 — SCALE
Employer benefit channel | Dev
Alexa skill v1 | Dev
Google Home action | Dev
AI voice conversation | Dev
FHIR expansion v2 | Dev
Pharmacy / Surescripts API | Dev
Trusted provider marketplace | Dev
Mobile app v2 | Dev
Plaid financial integration | Dev
Community & peer support | Dev
Phase 3 QA & scale test | Test
Phase 3 milestone ✓ | Launch | [26 empty] | ▲
PHASE 4 — EXPANSION
SOC 2 Type II certification | Dev
Clinical partnerships | Dev
Predictive health insights | Dev
Platform API (developer) | Dev
International — Canada | Dev
International — UK | Dev
Phase 4 milestone ✓ | Launch | [35 empty] | ▲
LEGEND
Development work |  | Testing / QA |  | Launch / milestone |  | Phase 0 — Foundation |  | Phase 1 — MVP |  | Phase 2 — Growth |  | Phase 3 — Scale |  | Phase 4 — Expansion

## Team & Resourcing
AGING GRACEFULLY — Team & Resourcing Plan
FTE headcount by role and phase. Contractors shown in italics. Assumes seed funding for Phase 0–1; Series A for Phase 2–3; Series B for Phase 4.
Role | Hire Phase | Ph 0 (1-3) | Ph 1 (3-9) | Ph 2 (10-18) | Ph 3 (19-27) | Ph 4 (28-36) | Total Yr 1 | Total Yr 2 | Total Yr 3
ENGINEERING
CTO / VP Engineering | Pre-seed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fullstack Engineer (web) | Phase 0 | 2 | 2 | 4 | 5 | 6 | 2 | 4 | 5
Backend / API Engineer | Phase 0 | 1 | 2 | 3 | 4 | 5 | 2 | 3 | 4
Mobile Engineer (iOS) | Phase 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 2
Mobile Engineer (Android) | Phase 1 | — | 1 | 1 | 2 | 2 | 1 | 1 | 2
DevOps / Platform Engineer | Phase 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 2
AI / ML Engineer | Phase 1 | — | 1 | 2 | 3 | 4 | 1 | 2 | 3
Data Engineer | Phase 2 | — | — | 1 | 2 | 2 | 0 | 1 | 2
Security Engineer | Phase 1 | — | 1 | 1 | 1 | 2 | 1 | 1 | 1
QA / SDET | Phase 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 2
PRODUCT & DESIGN
Head of Product | Pre-seed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Product Manager | Phase 1 | — | 1 | 2 | 3 | 4 | 1 | 2 | 3
UX Designer | Phase 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 2
UX Researcher | Phase 2 | — | — | 1 | 1 | 2 | 0 | 1 | 1
Accessibility Specialist | Phase 1 | — | 1 | 1 | 1 | 1 | 1 | 1 | 1
Content Strategist / Writer | Phase 1 | — | 1 | 2 | 2 | 2 | 1 | 2 | 2
CLINICAL & COMPLIANCE
Clinical Advisor (MD/RN) | Phase 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
HIPAA / Compliance Officer | Phase 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Data Privacy Officer (DPO) | Phase 2 | — | — | 1 | 1 | 1 | 0 | 1 | 1
Eldercare Content SME | Phase 1 | — | 1 | 2 | 2 | 2 | 1 | 2 | 2
GO-TO-MARKET
CEO | Pre-seed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Head of Marketing | Phase 1 | — | 1 | 1 | 2 | 2 | 1 | 1 | 2
Head of Sales (Employer) | Phase 2 | — | — | 1 | 1 | 2 | 0 | 1 | 1
Customer Success | Phase 1 | — | 1 | 2 | 3 | 4 | 1 | 2 | 3
Partnership Manager | Phase 2 | — | — | 1 | 2 | 3 | 0 | 1 | 2
Caregiver Community Manager | Phase 3 | — | — | — | 1 | 2 | 0 | — | 1
FINANCE & OPS
CFO (fractional → full-time) | Phase 1 | — | 1 | 1 | 1 | 1 | 1 | 1 | 1
HR / People Ops | Phase 1 | — | 1 | 1 | 1 | 1 | 1 | 1 | 1
Legal (external counsel) | Phase 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TOTAL HEADCOUNT |  | 13 | 25 | 42 | 52 | 66 | 25 | 42 | 52

## Testing Plan
AGING GRACEFULLY — Testing & QA Plan
Test type | What's tested | Tools / method | Frequency | Gate | Pass criteria
AUTOMATED TESTING (continuous)
Unit tests | All business logic functions, data transformations, utility functions, FHIR normalization | Jest (TS), pytest (Python services), coverage >85% | Every commit | CI gate — blocks merge | >85% coverage; 0 failures
Integration tests | API endpoints, database interactions, service-to-service calls, auth flows | Jest + Supertest; test containers for DB | Every PR | CI gate — blocks merge | All endpoints return correct status; auth enforced
Accessibility (automated) | WCAG 2.2 violations: contrast, missing labels, keyboard traps, ARIA errors | axe-core in Jest; Lighthouse CI | Every PR | CI gate — zero new violations | axe: 0 new violations; Lighthouse a11y ≥ 95
Security scan (SAST) | Code-level vulnerabilities: SQLi patterns, hardcoded secrets, dependency CVEs | Snyk SAST + Dependabot | Every PR | Blocks merge if high/critical CVE | 0 high/critical CVEs in production code
E2E smoke tests | Critical user journeys: sign up, upload document, share emergency packet, AI Q&A | Playwright (headless Chrome + Firefox + Safari) | Every deploy to staging | Blocks production deploy if failing | All smoke tests green
Performance regression | LCP, TTI, bundle size — must not regress from prior deploy | Lighthouse CI + custom bundle size check | Every deploy to staging | Blocks deploy if regression >10% | LCP <2.5s; bundle <250KB gzipped
SPRINT / RELEASE TESTING
Functional QA | Full feature testing against acceptance criteria for every user story in the sprint | Manual test cases in TestRail; exploratory testing | Every sprint (2 weeks) | Release gate — no P0/P1 open | All ACs met; <5 P2 bugs; 0 P0/P1
Regression testing | Full regression suite on staging before every production release | Playwright E2E suite (400+ tests by MVP) | Pre-release (weekly from Phase 2) | Production deploy gate | 0 regressions vs. last release
Cross-browser / device | Chrome, Firefox, Safari, Edge; iOS Safari, Android Chrome; tablet layouts | BrowserStack automated grid | Every release | Release gate | No P1+ defects on supported browsers
API contract testing | GraphQL schema changes do not break existing clients; REST versioning | Pact.io contract tests; GraphQL schema linting | Every PR touching API | CI gate | All consumer contracts passing
Data integrity | Document upload/download hash match; FHIR normalization accuracy; audit log completeness | Custom test suite comparing input/output hashes | Sprint integration tests | Release gate | 0 hash mismatches; audit log 100% complete
MILESTONE TESTING (per phase)
Load testing | Simulate target concurrent users; identify bottlenecks before scale | k6; target: 5k concurrent (MVP), 50k (Ph2), 100k (Ph3) | End of each phase | Phase milestone gate | P95 API response <500ms at target load
Penetration testing | External attack surface: auth, API, file upload, prompt injection, SMS spoofing | Third-party pen test firm (annual); internal DAST quarterly | Annually + pre-major launch | Phase milestone gate | No critical/high findings unresolved
Accessibility (manual) | Screen reader workflows with real users; keyboard-only navigation; switch access | NVDA/JAWS/VoiceOver; testers who use AT daily | Quarterly (CPACC-certified specialist) | Phase milestone gate | All critical journeys operable; 0 WCAG AA violations
HIPAA / Compliance audit | Data handling, access controls, audit log, BAA coverage, breach response | Internal compliance team + external HIPAA counsel | Annually | SOC2 observation milestone | 0 material HIPAA findings
FHIR conformance testing | FHIR server responses validate against R4 spec; SMART auth compliant | Inferno FHIR testing tool; HL7 FHIR validator | Before each EHR integration goes live | EHR go-live gate | All Inferno tests pass; 0 critical conformance failures
Chaos engineering | Simulate: database failover, S3 outage, AI API timeout, network partition | Gremlin chaos experiments on production-like staging | Quarterly | Phase 3 milestone gate | Graceful degradation; RTO within SLA
Disaster recovery drill | Full production failover to secondary region; data recovery test | Manual runbook execution timed drill | Bi-annually | Phase 3+ milestone gate | RTO <1hr; RPO <15min; all data intact
User acceptance testing | Real caregiver families validate feature completeness and usability | Structured UAT sessions (moderated) + diary studies | Before each phase launch | Phase launch gate | NPS >60 (MVP); >65 (Ph2); >70 (Ph3)
SPECIALIST TESTING
AI safety / output validation | Hallucination rate, medical advice accuracy, PII leakage in responses, prompt injection resistance | Red-team testing; medical expert review of sample outputs; automated PII scanner on responses | Monthly + before AI feature launches | AI feature launch gate | <2% hallucination rate; 0 PII in AI responses; prompt injection blocked
SMS / voice compliance | TCPA opt-out processing, quiet hours enforcement, message frequency limits, carrier delivery rates | Twilio test numbers; carrier sandbox; manual STOP testing | Before SMS launch + quarterly | SMS feature launch gate | STOP processed in <5s; 100% quiet hours compliance; >95% delivery rate
Financial data security | Plaid token handling, bank data encryption, anomaly detection accuracy, access revocation | Security review + Plaid sandbox testing | Before financial integration launch | Plaid integration gate | 0 unencrypted financial data; revocation works in <1min

## Launch Checklist
AGING GRACEFULLY — MVP Launch Checklist (Month 9)
Category | Item | Owner | Due | Status
ENGINEERING — PRODUCTION READINESS
All P0/P1 bugs resolved |  | Engineering Lead | Week -2 | Not started
Load test passed (5,000 concurrent users) |  | DevOps | Week -2 | Not started
Security penetration test — no critical/high open |  | Security Eng | Week -3 | Not started
WCAG 2.2 AA audit — 0 violations |  | Accessibility Spec | Week -2 | Not started
Automated test suite >85% coverage; all passing |  | QA Lead | Week -1 | Not started
Disaster recovery drill completed — RTO <1hr |  | DevOps | Week -3 | Not started
Database backups verified + cross-region replication |  | DevOps | Week -1 | Not started
All secrets rotated to production KMS keys |  | Security Eng | Week -1 | Not started
CDN & WAF configured; DDoS protection enabled |  | DevOps | Week -1 | Not started
On-call rotation and PagerDuty escalation configured |  | Engineering Lead | Week -1 | Not started
Runbooks for all P1 alert conditions documented |  | DevOps | Week -2 | Not started
Feature flags configured; kill switches tested |  | Engineering Lead | Week -1 | Not started
LEGAL & COMPLIANCE
Privacy policy live at /privacy (CCPA + GDPR-ready) |  | Legal | Week -3 | Not started
Terms of service live and reviewed by counsel |  | Legal | Week -3 | Not started
HIPAA Business Associate Agreement with AWS signed |  | Legal + CTO | Week -4 | Not started
HIPAA BAA with Anthropic (AI) signed |  | Legal + CTO | Week -4 | Not started
10DLC SMS brand registration approved by carriers |  | Legal + Eng | Week -4 | Not started
TCPA compliance review completed |  | Legal | Week -3 | Not started
Cookie consent (Cookiebot) live and configured |  | Engineering | Week -2 | Not started
Data processing agreements with all sub-processors |  | Legal | Week -4 | Not started
Incident response plan documented and tested |  | CISO | Week -3 | Not started
Cyber liability insurance policy active |  | CFO | Week -4 | Not started
PRODUCT & CONTENT
All MVP features complete per acceptance criteria |  | Head of Product | Week -2 | Not started
Onboarding flow tested with 20+ real users |  | UX Research | Week -3 | Not started
Error messages — all P0 user journeys have helpful errors |  | Product / Eng | Week -2 | Not started
Empty states for all core screens (no blank pages) |  | Design | Week -2 | Not started
Help center / FAQ live with 30+ articles |  | Content | Week -1 | Not started
All health content reviewed by clinical advisor (MD/RN) |  | Clinical Advisor | Week -3 | Not started
All legal content (advance directives) reviewed by attorney |  | Eldercare Attorney | Week -3 | Not started
AI output review — 50+ sample outputs reviewed for accuracy |  | Clinical + AI Eng | Week -2 | Not started
Email templates (welcome, alerts, reminders) designed + tested |  | Marketing + Eng | Week -2 | Not started
Mobile app submitted to App Store + Google Play |  | Mobile Eng | Week -3 | Not started
App Store / Play listing copy and screenshots complete |  | Marketing | Week -3 | Not started
MARKETING & LAUNCH
Launch press release drafted and distributed |  | CEO + Marketing | Launch day | Not started
Product Hunt launch prepared (hunter, assets, copy) |  | Marketing | Week -1 | Not started
Landing page with waitlist / sign-up live |  | Marketing + Eng | Week -4 | Not started
SEO — meta titles, descriptions, OG tags on all key pages |  | Marketing | Week -2 | Not started
Social media accounts live (LinkedIn, Instagram, Facebook) |  | Marketing | Week -2 | Not started
Email list (waitlist) ready for launch announcement |  | Marketing | Launch day | Not started
Caregiver advisor / influencer outreach completed |  | Marketing | Week -2 | Not started
Press kit (logos, screenshots, founder bio, fact sheet) |  | Marketing | Week -1 | Not started
Google Analytics + Mixpanel analytics live and tracking |  | Marketing + Eng | Week -2 | Not started
Customer support tooling (Intercom) configured |  | Customer Success | Week -2 | Not started
CUSTOMER SUCCESS & SUPPORT
Support team trained on all MVP features |  | CS Lead | Week -2 | Not started
Escalation paths defined (Tier 1 → Tier 2 → Engineering) |  | CS Lead | Week -2 | Not started
NPS survey configured (trigger at Day 14) |  | CS + Product | Week -1 | Not started
Feedback button live on all screens |  | Product + Eng | Week -2 | Not started
User onboarding email sequence configured (5-email drip) |  | Marketing + CS | Week -2 | Not started
Beta user migration plan — all 50 beta families invited |  | CS Lead | Week -1 | Not started
Status page live (status.agingracefully.com) |  | DevOps | Week -2 | Not started

## Success Metrics
AGING GRACEFULLY — Success Metrics & KPIs by Phase
Metric | MVP (Mo 9) | Phase 2 (Mo 18) | Phase 3 (Mo 27) | Phase 4 (Mo 36) | How measured
GROWTH & ACQUISITION
Active families (MAU) | 1,000 | 10,000 | 50,000 | 150,000 | Mixpanel / product analytics
Monthly signups | 200 | 500 | 2,000 | 5,000 | Analytics dashboard
Organic / paid split | 80% organic | 70% organic | 60% organic | 55% organic | UTM tracking
Employer accounts | 0 | 5 pilots | 100 accounts | 300 accounts | CRM (Salesforce)
App Store rating | ≥ 4.0 | ≥ 4.3 | ≥ 4.5 | ≥ 4.6 | App Store Connect / Play Console
ENGAGEMENT & RETENTION
D30 retention | 40% | 50% | 60% | 65% | Cohort analysis in Mixpanel
D90 retention | 25% | 35% | 45% | 55% | Cohort analysis
Weekly active users / MAU | 35% | 45% | 55% | 60% | Product analytics
Docs uploaded per family (avg) | 3 | 8 | 12 | 15 | SQL query on documents table
AI queries per active user / week | 2 | 5 | 8 | 10 | AI usage logging
SMS parent interactions / week (Ph2+) | — | 3 per enrolled parent | 4 per enrolled parent | 5 per enrolled parent | Twilio message logs
QUALITY & SATISFACTION
Net Promoter Score (NPS) | ≥ 60 | ≥ 65 | ≥ 70 | ≥ 72 | Delighted survey at Day 14 + quarterly
Customer satisfaction (CSAT) | ≥ 4.0 / 5.0 | ≥ 4.2 / 5.0 | ≥ 4.4 / 5.0 | ≥ 4.5 / 5.0 | Post-support survey
Support ticket volume / 1k MAU | < 50 / mo | < 35 / mo | < 25 / mo | < 20 / mo | Intercom dashboard
AI accuracy (user thumbs up rate) | ≥ 80% | ≥ 85% | ≥ 90% | ≥ 92% | AI feedback logging
Accessibility score (Lighthouse) | ≥ 95 | ≥ 97 | ≥ 97 | ≥ 98 | Lighthouse CI dashboard
REVENUE & BUSINESS
Annual Recurring Revenue (ARR) | $0 (beta) | $1M | $5M | $20M | Stripe + billing dashboard
Average Revenue Per User (ARPU) | — | $100 / yr | $100 / yr | $133 / yr | ARR divided by MAU
Gross margin | — | ≥ 65% | ≥ 72% | ≥ 78% | Finance dashboard
Customer Acquisition Cost (CAC) | — | < $80 | < $60 | < $50 | Marketing attribution model
LTV:CAC ratio | — | ≥ 3:1 | ≥ 5:1 | ≥ 7:1 | Finance model
Employer contract value (ACV) | — | $10k / yr avg | $20k / yr avg | $30k / yr avg | CRM
TECHNICAL & COMPLIANCE
Platform uptime | ≥ 99.9% | ≥ 99.9% | ≥ 99.9% | ≥ 99.95% | Datadog SLO dashboard
API P95 latency | < 500ms | < 400ms | < 300ms | < 250ms | Datadog APM
AI response P95 (first token) | < 4s | < 3s | < 2.5s | < 2s | Custom AI latency metric
Security incidents (P1) | 0 | 0 | 0 | 0 | Security incident log
HIPAA audit findings (material) | 0 | 0 | 0 | 0 | Compliance audit reports
SOC 2 status | Type I in progress | Type I complete | Type II in progress | Type II certified | Audit firm certification